## Sheet1
ISSUE TRACKER FOR AR / VR
S/N | ISSUE DESCRIPTION | STATUS | PLATFORM | RESPONSIBLE | DURATION | START DATE | END DATE
1 | Changing a name of system | Not Started | WEB | EMMANUEL ACHILLES | 1 | 2024-06-05 | 2024-06-05
2 | Making tours to be visible first | Not Started | WEB | EMMANUEL ACHILLES | 1 | 2024-07-05 | 2024-07-05
3 | Changing words from the welcoming page | Not Started | WEB | EMMANUEL ACHILLES | 1 | 2024-07-05 | 2024-07-05
4 | Our service should be the last part in landing page | Not Started | WEB | EMMANUEL ACHILLES | 1 | 2024-08-05 | 2024-08-05
5 | In profile image, should show all the image formats | Not Started | WEB | EMMANUEL ACHILLES | 1 | 2024-08-05 | 2024-08-05
6 | File input, should show all the file formats supported in the system | Not Started | WEB | PIUS BARAKA | 1 | 2024-06-05 | 2024-06-05
7 | Add delete feature in tours | Not Started | WEB | PIUS BARAKA | 1 | 2024-06-05 | 2024-06-05
8 | Add upload feature in approved tours | Not Started | WEB | EMMANUEL ACHILLES FRANK ILUNGA | 1 | 2024-09-05 | 2024-09-05
9 | Listing tours when added in add panorama | Not Started | WEB | PIUS BARAKA | 2 | 2024-07-05 | 2024-08-05
10 | Add cancel feature when adding scene | Not Started | WEB | PIUS BARAKA | 1 | 2024-09-05 | 2024-09-05
11 | Adding add feature in file input page | Not Started | WEB | PIUS BARAKA | 1 | 2024-09-05 | 2024-09-05
13 | Adding a system theme color | Not Started | WEB | YOLANDA DIDAS | 3 | 2024-07-05 | 2024-09-05
14 | Integration with ivr.all.tz | Not Started | WEB | CLAUD CHARLES | 1 | 2024-10-05 | 2024-10-05
15 | Development of landing and splash screen | Not Started | MOBILE | SAVIO KALINGA | 1 | 2024-06-05 | 2024-06-05
16 | Development of home screen, scenes and settings | Not Started | MOBILE | SAVIO KALINGA | 1 | 2024-06-05 | 2024-06-05
17 | Search optimization using virtual tour or location | Not Started | MOBILE | SAVIO KALINGA | 1 | 2024-06-05 | 2024-06-05
18 | Create platform for registration and login | Not Started | MOBILE | SAVIO KALINGA | 3 | 2024-07-05 | 2024-09-05
19 | Showing all tours from web | Not Started | MOBILE | PAUL MICHAEL | 3 | 2024-06-05 | 2024-08-05